## Slide 1: Status SLS 2.0
Hans Braun :: Paul Scherrer Institut
Sitzung Leitender Ausschuss Beschleunigeranlagen, 6.11.2020

## Slide 2: SLS 2.0, Ziele und Methoden
Ziele: Massiv höhere Strahlbrillianz / Photonenflussdichte
 bessere räumliche Auflösung
 wesentlich höhere Kohärenz der Röntgenstrahlung
 schnellere Experimentdurchführung
Erweiterung Photonen-Energiebereich zu kürzeren Wellenlängen
 bessere Durchdringung, bzw. dickere Proben möglich
Methoden: Neues Synchrotron im existierenden Tunnel mit «MBA» Magnetanordnung
Erhöhung der Strahlenergie 2.4 GeV 2.7 GeV
Neue Undulatormagnete
Drei supraleitende «Superbend» Magnete mit bis zu 5.5 Tesla Ablenkfeld
Neue oder neukonfigurierte bzw. verbesserte Strahllinien
Neue Konzepte zur Datenerfassung und Verarbeitung

## Slide 3: SLS
SLS today
  Circumference 288 m
  3× long, 3× medium, 6× short straights
  total straight length  80 m
  Beam current 400 mA
  Beam energy 2.41 GeV
  Emittance 5500 pm
SLS 2.0
maintained
  Circumference 288 m
  3× long, 3× medium, 6× short straights
  total straight length  80 m
  Beam current 400 mA
almost maintained
  Source point positions |shifts| < 70 mm
improved
  Emittance 157 pm (from 5500 pm)
  Energy 2.7 GeV (from 2.41 GeV)
SLS → SLS 2.0

## Slide 4
SLS 2.0
SLS now
7 bend MBA
TBA

## Slide 5: Vorteil SLS TBA*  SLS2.0 MBA**
Vereinfacht zusammengefasst:
Neue Synchrotrons bestehen aus vielen kleinen und komplizierten Magneten, statt aus wenigen grossen, einfachen Magneten
Vorteil:
* TBA = Triple Bend Achromat ** MBA = Multi Bend Achromat

## Slide 6: Beamline layout
Injection
01
02
03
04
05
06
07
08
09
10
11
12
i-TOMCAT
RIXS
MS
XIL. SX-ARPES
PX I
XTreme/
Phoenix
PX III
PolLux/
nanoXAS
s-TOMCAT
PX II
SIM
cSAXS
SuperXAS
short straight
medium straight
long straight
superbend
normal bend
Optics/
Diagnostcs
VUV
microXAS
SuperARPES
Debye
NAPP 2027
ID list 2: 1-m U10 (U14 fallback) 3: 4.5-m UE36 K-not 4: 2-m U14, later 1-m U10? 5: 3.5-m UE32 K-not + 2-m UE48 6: 3-m U15 7: 4.5-m or 2 x 2-m UE36 8: 3-m U15 9: 3-m UE36 K-not + 4.5-m UE90 K-not 10: 3-m U15 11: 4.5-m or 2 x 2-m UE36 Knot 12: 3-m U15
3-5 T
3-5 T
3-5 T
2 T
BL relocations
Stays
Moves
New

## Slide 8: SLS 2.0 Aktivitäten 2020
Zahlreiche Aktivitäten zu Komponentendesign und Prototypenbau
Vorbereitung Ausschreibungen für Speisegeräte, Magnete, Vakuumkammern, HF Anlagen…
Optimierung Abbau- / Aufbauplanung
Vorbereitung Einbau zweiter Kran in SLS
Suche temporäres Lager- und Montagegebäude ausserhalb PSI
Aufbau neue Projektstruktur für Umsetzungphase 2021-2026
Finalisierung Ringdesign
Finalisierung Beamline Auswahl und Anordnung
Aufbau 3D Modell
Entscheid Energieerhöhung 2.4GeV  2.7 GeV
Up-date Kostenschätzung
Erste Schritte Strahlenschutzstudien und BAG Bewilligungsprozess
Start TDR Dokument
…
Finaler Finanzierungsentscheid im Rahmen BFI Botschaft erwartet für Dezember 2020

## Slide 9: Permanent magnets
VB combined function
BN main dipole
1.35 T
AN reverse bend (=off centered quadrupole)
NdFeB permanent magnet blocks and NiFe strips for tuning

## Slide 10: First SLS2.0 full-scale permanent magnet prototypes at PSI
Preparing first BN magnet for field measurement
First full-scale SLS2.0 PM magnet prototype (Type BN)
First full-scale SLS2.0 VB magnet prototype
Highly sophisticated PM magnet block sorting panel

## Slide 11: Electromagnets
SOQ
sextupole + octupole
with regular and skew quadrupole correctors
QP quadrupole
100 T/m
CHV orbit corrector
top view

## Slide 12: Superbends
BS5
5 Tesla SC-dipole
BS2
2 Tesla PM-dipole

## Slide 13: Design Concepts modular in-Vacuum Undulator
modules on a girder
combined function: vacuum chamber & support
multiple drive units (hydraulic)
(low forces, compact)
profit from high machining precision
reduced parts
variable length
cost effective
many suppliers

## Slide 14: HTS10 for i-Tomcat & MS
U15 RT
HTS10

## Slide 15: HTS progress
Collaboration Agreement
PSI - FermiLab
12T Superconducting Solonoid
magnetic length: 1m
solonoid: 1.5m
transition section 2x 300mm
straight 2
to be shared with injection kickers
max. 2m long cryostat

## Slide 16: Athos UE38 Apple X → same for SLS2.0 long straights?

## Slide 17: SLS 2.0 brightness
Improvement factors relative to SLS:
reduced emittance: × 24 (10...20 keV)
+ higher energy (2.7 GeV): × 59 (10...20 keV)
+ new undulator (CPMU15 instead of U19): × 140 (10 keV) ... 870 (20 keV)
+ upgrade to SCU10: × >1000 above 20 keV
Calculations and plot by Thomas Schmidt

## Slide 18: Vacuum Chamber design SLS2.0
Top Cut View of a SLS2.0 Vacuum Arc (near Superbend)
12 arcs => 500 Chambers (mainly in copper)
1 mm wall thickness & 18 mm inner diameter
Constrains: Space – Heat Load – Synchrotron Light Extraction - Impedance

## Slide 19: Arc Vacuum Chambers
CSS: Chamber Straight Steerers
Octagonal; d=21mm
Stainless Steel, L=130mm
5 um copper coating
0.5 um NEG
CBN: Chamber Bend Normal
Slit = 3 mm for Extraction
Octagonal; d=18mm
Cu OFE, L=1431mm, Wallmin=1mm
0.5 um NEG
CBI: Chamber Bend IN
Slit = 10 mm for Extraction
Octagonal; d=18mm
Cu OFE, L=991mm
0.5 um NEG
CRM: Chamber Reverse Middle
No Slit
Octagonal; d=21/18mm
Cu OFE, L=563mm, Wallmin=1mm
0.5 um NEG
CSU: Chamber Straight Upstream
Octagonal; d=18mm
Cu OFE, Wallmin=1mm
0.5 um NEG
No bellows; 2 End Gate Valves
Flat gaskets (Vatseal)
7 Ion Getter Pump & 7 NEG Capacitorr

## Slide 20: CBN Prototype Production at PSI
1. Pre-machining
  Forged Cu – OFE (CW009A)
  Water Cut to approximate shape
2. Copper Machining
  Rough milling and subsequent
  stress free annealing
  Fine milling (Vacuum Holding Support)
  - 1 mm wall thickness
3. External procurement:
  Stainless steel cube
  flanges
Air-conditioned room and cooling water regulation for stable production conditions
Courtesy of René Siebert
To be ready by December 2020

## Slide 21: Moving solenoid NEG coating setup
Coating Setup under commissioning
October 2020: 1st NEG coating over 1.5 m length

## Slide 22: SLS2.0 work done so far

## Slide 23: SLS2.0 work done so far

## Slide 24: Schedule concept
Tunnel
Closure
Start Dark-Time
Start Gr. 1 Beamline commissioning
Start Gr. 1 user operation
Start Gr. 2 Beamline commissioning
Start Gr. 2 user operation
Point of no return

## Slide 25: Reasoning for two group schedule concept
  Superbends are the magnets with the highest risk to arrive late because of novel design & first SC magnets designed by PSI magnet section. Maybe modifications required after first prototype test anticipated for late 2023. Two group concept gives the slack to mitigate schedule risks due to the superbends.
  Beam dynamics commissioning team doesn’t want to mix the very evolved first beam based optics correction with specific issues of superbend commissioning.
  The second 3 month shutdown in 2026 reduces workload in 2024, thus permitting tunnel closure 15 month after start of dark time and first user experiments 22 month after start of dark time.
  Resource loading for beamline work more relaxed.
  More opportunities to beef up beamline budget with SNF R’Equip grants.
  Installation planning team believes that tunnel closure end 2024 is possible with this scheme.
  Group 2 has a dark period without user operation of 34 month

## Slide 26
SLS 2.0 Organigramm

## Slide 27: Status new cost estimate
Raw data collection completed 28 September
Budget workshop with all subproject leaders on 13 october
Long follow-up list still to be processed before budget estimate can be consolidated!
Time
Problem: the known available budget is 116 MCHF

## Slide 28: Änderungen an der SLS vor SLS-2.0
Projekte mit Budgetierungen unabhängig von SLS-2.0 Zeitplan & Umfang z.T. noch nicht definitiv
zwei neue Strahllinien: Debye, I-Tomcat
Änderung S-Tomcat: Bau einer Optik-Hütte (Blei) mit PSYS aussen am Ringtunnel um bestehendes, abgeschirmtes Strahlrohr in 2021
Umbau Userareal PX III: Änderung Raumaufteilung, Vergrösserung Endstation 06D (keine wesentlichen Eingriffe in Ringtunnel oder Optikhütten), Pilot für SLS-2.0 Technologie, Beginn Inbetriebnahme ca. Ende 2022

## Slide 29
Danke für Eure Aufmerksamkeit
und
Dank an alle deren Folien ich gezeigt habe