## Slide 1: SwissFEL Exchange Meeting Machine report Week 16/2021
Didier Voulot, SEM, 26 April 2021

## Slide 2: Start-up
Wednesday:
  Machine cold checks
  Tunnel closed 12:30
  RF start-up and laser set-up
Thursday
  Phasing and transmission Aramis
  RF puslse setting for two-bunch operation (Qiao)
  BPM set-up and commissioning (Boris)
Friday
  Aramis lasing set-up, 11.2 keV 560 uJ (Simona)
Saturday
  2-bunch set-up emittance and bunch length checks
  Transmission through Athos dogleg
Sunday
  Transmission through Athos undulators (losses)
  MD shift: Passive streaker tool test (Philipp and Eduard)

## Slide 3: Technical difficulties
Difficulties with PSSS set-up, problems with motor controls/homing
Disconnected channel on MMM logic prevents valid mode for Athos, finally solved with a VME power cycle (the PLC was actually ok)
No monitors in Snapshot. Some magnets channels were disconnected after power cycling the VME the channels came back and Snapshot was good again. Not sure if the two problems were really connected. Maybe just a coincidence. (The problem was present for all sort of req files also files without magnet channels.)
Problems with the diffusor logic. Could not be opened (soft-MPS alarm).

## Slide 4: Lessons learnt
Should always start with the 2-bunch set-up. Starting with Aramis and then doing Athos is a bad idea. We end up with a poorly set-up bunch2 (energy error in both chicanes) or have to redo the Aramis tuning.
Doing the set-up during the weekend is not efficient. Many technical problems could be resolved much faster if experts would be available.