## Slide 1: Diavolezza Update
SwissFEL Performance Workshop
S. Neppl – Laboratory for Nonlinear Optics
SwissFEL Performance Workshop, Windisch/Brugg, January 21st 2025

## Slide 2: Diavolezza project structure
Project Leader
Stefan Neppl
HL/KB system Rolf Follath
Layout/3D Dominique Hauenstein
Optics/HOM Ulrich Wagner
Diagnostics Chris Arrell
Installation/ Coordination Erich De Boni
Beamline
Claude Pradervand
Endstation
Stefan Neppl
Working Group
Martin Huppert
(Hutch/Experiment Layout)
Yunpei Deng
(Laser System/Transport)
Juraj Krempasky
(DAQ)
Project Owner Adrian Cavalieri
(for beamline)
Funding: R’Equip (09/2022) 1800 kCHF
Funding: currently LNO budget

## Slide 3: Diavolezza beamline
KB mirror
Furka
Hor. Offset mirror
OPAU,OLIR,PSCA
OLAS,OLIR
OSCR
PSCR
Athos optics hutch UH.026
Diavolezza hutch EH.030a
OPSH
OPAU, PSCR
OEXS, PMOS
OSCR
Diavolezza
Hor. Offset mirror
(2° deflection)
Maloja
Furka
Layout finalized; HL frozen

## Slide 4: Timeline Diavolezza beamline (coarse)
Hor. offset mirror
KB system
Diagnostics
2024 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  | 
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 1 |  | 2 | 3 | 4 | 5 | 6
Vacuum (standard)
FDR
KB optics
Kick-off
PDR
Design/Specification
Fabrication (in house)
Installation (SD)
PDR
Design/Specification
FDR
Fabrication (TOYAMA)
Shipment/Installation
FAT
SAT
Specification
Procurement/Production
Installation
Design/Specification
Procurement/Delivery
Installation
Specification
Procurement

## Slide 5: Diavolezza endstation layout
Athos pump laser I
800 nm
2-15µm
OPA
Compr.
Control Room (EH.030b)
DIAVOLEZZA Hutch
(EH.030a)
800 nm
Furka
Maloja
THz setup
Mid streaking setup
Open port
HCF
Athos pump laser II
800 nm
Compr.
OPA
1-2µm
CMC
FEL
Broadband XUV
Phase-II (>2028)
Toroidal XUV mirror
KB mirror

## Slide 6: THz streaking setup
∆t = 130 fs
∆E = 80 eV
S = 0.6 eV/fs
Tests @ Maloja (05/2023)
Athos standard pulse mode
50 ± 10 fs
180 fs

## Slide 7: Mid-IR streaking setup
TOF #2
TOF #1
focal plane
e-
e-
Gouy phase shift
Rayleigh length
Rayleigh length
FEL
Mid IR
FEL
Mid-IR
14 µm
Approach:
Self-referencing to mitigate timing jitter
Dual gas nozzle
10-6 mm

## Slide 8: Mid-IR streaking setup
TOF #2
TOF #1
focal plane
e-
e-
Gouy phase shift
Rayleigh length
Rayleigh length
FEL
Mid IR
Streak field
@ TOF #2
Streak field
@ TOF #1
Delay Delay/Shot No. ΔKE TOF #1
Field Strength
ΔKE TOF #1 Δ KE TOF #2
Δ KE TOF #2
Streak Field Energy Shift Correlation
Approach:
Self-referencing to mitigate timing jitter
Simulation:
phase shift
CEP stable mid-IR
Perfect mid-IR/FEL
synchronization

## Slide 9: Mid-IR streaking setup
TOF #2
TOF #1
focal plane
e-
e-
Gouy phase shift
Rayleigh length
Rayleigh length
FEL
Mid IR
Delay Delay/Shot No. ΔKE TOF #1
Field Strength
ΔKE TOF #1 Δ KE TOF #2
Δ KE TOF #2
Streak Field Energy Shift Correlation
Streak field
@ TOF #2
Streak field
@ TOF #1
Approach:
Self-referencing to mitigate timing jitter
Simulation:
phase shift
CEP stable mid-IR
Timing jitter
t
t

## Slide 10: Mid-IR streaking setup
Retrieved Ne1s spectrogram
Ne1s-Ne1s correlation
(~70.000 shots)
Tests @ Maloja (07/2024)
Athos low bunch current mode (20pC)
Passive CEP stable mid-IR (twinTOPA)
Mean 4.5 fs
Single-shot pulse
durations evaluated near
mid-IR zero-crossings
Notes: Composed of ca. 70.000 single shots

## Slide 11: Summary & Outlook
Beamline:
Layout/design finalized; start of installation 2025
KB mirror system in production
Horizontal offset mirror in production
First focused beam in Diavolezza hutch expected in Q2/Q3 2026
Endstation:
Specification of laser infrastructure finalized
Hutch experimental layout finalized
THz and mid-IR setups successfully tested
To do:
Installation of basic media distribution in Diavolezza hutch
Design and construction of laser enclosure (Q2-Q4 2025)
Design and tests of chamber supports (Q4 2025)
Procurement and test of DAQ (10 GS/s digitizers), Laser components etc.
New eTOF design with higher resolving power & retardation (Q1 2026)

## Slide 12
Thank you for your attention!
HH generation
KB mirror
Pump laser conversion
/distribution
THz setup
MIR setup
Space for roll-up experiments
(open port)