Commissioning Phases
The commissioning can divided into seven phases:
- Phase 1 – Linac, booster and transfer line commissioning
- Phase 2 – First-turn in storage ring
- Phase 3 – Second-turn and multi-turn
- Phase 4 – Accumulation, basic feedbacks and linear optics
- Phase 5 – Nominal beam current with advanced settings and feedbacks
- Phase 6 – Insertion device and collimator setup, making first photon beams
- Phase 7 – Finalization

---
Commissioning Phases and Shifts
Distribution of shifts (5*12h day shifts / week) over the different phases :
- Phase 2 – 1 (+3)
- Phase 3 – 1
- Phase 4 – 8 (+3) → setting up of safe and emergency beam dump
- Phase 5 – 15 (+5) → most critical phase reaching nominal beam current
- Phase 6 – 9
- Phase 7 – 10
Phase 4: <100 mA dumped slowly with MBFB or fast kicker
In 2001 the dose of 100 Ah was needed for the vacuum conditioning of SLS (Target: 2 *10e-9 mbar):
→In total 44 (+11) shifts corresponding to 11 weeks (~3 months)
→Assuming 30 night shifts (6 weeks) at 400 mA
→ accumulated 144 Ah
L. Schulz
SLS
SLS 2.0
R. Ganter
CO equiv
Dynamic Pressure dP/dI vs accumulated dose (N2 equiv)
Expecting same dP/dI for SLS 2.0 !

---
High & Intermediate level BD applications for SR commissioning
- P2: Measurement of injected beam trajectory (*)
- P2-3: Beam Threading and BPM offset discrimination
- P4: Lifetime Measurement (IPCT / Loss Monitors)
- P4: Tune Measurement / Adjustment *
- P4: Dispersion & Chromaticity Measurement & Correction *
- P4: Emittance Measurement (Controller) (*)
- P4: BBA Beam-Based Alignment (Slow (>P7: Fast)) (*)
- P4: BBGA Beam-Based Girder Alignment *
- P4: Optics correction (LOCO/Quad Variation/Turn-by-Turn) *
- P4: Orbit Correction (SOFB (P5: FOFB)) inc. frequency *
- P4: Nonlinear Optimizer → DA and lifetime *
- P6: Insertion Device Feed-Forward (orbit / optics) *
The applications have to bring us through the commissioning phases 2-6.
Consolidation does not have a priority.
Applications will change during the commissioning while we gain experience.
We concentrate on the physics and find solutions.
Applications requiring offline analysis are ok.
Phase 4 (P4) ~ 3 months
* requiring model online or offline