## Slide 1: Updates on WPMAG
WPMAG Final Meeting 2025
Valentina Corato
ENEA- Frascati

## Slide 2: Outline
DEMO-LAR Gate Review 2025
Work Plan for 2026-27
Grant Deliverables and Milestones
Project Deliverables
Resources and task specifications 2026
WPMAG meetings

## Slide 3: Gate Review G2a
Aim: status assessment and identification of critical issues and showstoppers of DEMO Low Aspect Ratio baseline (DEMO-LAR).
Date: 17-20 November 2025
Attendee’s Name | Attendee’s Role / Comments
Benoît Salamon | Panel Chairman
Stefano Chiocchio | Panel Member
Neil Mitchell | Panel Member
Jean Pierre Friconneau | Panel Member
Raphael Mitteau | Panel Member
Alfredo Portone | Panel Member
Antonino Cardella | Panel Member
Sara Villari | Panel Member
Laurence Williams | Panel Member
Karine Liger | Panel Member
Francis Casson | Panel Member
Nobuyuki AIBA | Panel Member
Marco Wischmeier | Panel Member
Marco De Baar | Panel Member
 | Session 03 Feasibility of magnet system |  |  | 
3.1a | DEMO -LAR, comparison with previous DEMO baseline 2SY6XN | 14:05 | 10’ | C. Luongo
3.1b | Magnet system summary: TF, CS, PF coil designs and supporting analyses 2SY4BF | 14:15 | 20’ + 20’ | L. Giannini
3.2 | Feasibility of manufacturing, transport, assembly 2SYDWX | 15:05 | 10’ + 15’ | P. Bruzzone
3.3 | Key Supporting Technologies: R&W and HTS conductor development 2SYCQL | 15:45 | 25’ + 15’ | V. Corato
3.4 | Medium-term HTS qualification program: plans and collaborations 2SYAU6 | 16:25 | 10’ + 15’ | C. Luongo
Thank you sincerely for your dedication and hard work in completing the designs and analyses in time for the gate review !!

## Slide 4: Gate Review G2a: Magnetic cage
The panel will make recommendations along the following lines :
  A deeper consideration should be given in the system code to the detailed-design and manufacturing driven size increase (intercoil structures, operationnal gaps, etc…)
  The modification of mechanical design codes safety criteria seems not to be sound at a pre-conceptual stage.
  The research on HTS magnets could be converged on one or two specific qualified HTS conductor designs, become less concentrated on extremely high field pulsed conductor performance and extended to include the critical new coil technologies being proposed.

## Slide 5: Gate Review G2a: Next steps declared at G2a
EC 2026–2027 programme funds Fusion Pilot Plant, not DEMO.
EUROfusion Central Team refocuses on Pilot Plant conceptual design.
VNS identified as one candidate option.
Pilot Plant development and construction could run in parallel with ITER.
Conceptual design phase planned for 2026–2027, with a design review in 2027.
The EUROfusion work plan explicitly distinguishes short-term activities focused on the Pilot Plant and long-term activities focused on a future first-of-a-kind power plant similar to DEMO Phase 2. Roughly 50% of resources will be dedicated to each. While the Central Team will concentrate on the Pilot Plant conceptual design, physics activities and long-term technology development will continue to support the future power plant.

## Slide 6: Plan for WPMAG System Design
The magnet design at pre-conceptual level has been completed
For Baseline 2018
Innovative variants for TF, CS, and PF coils (high current version wrt 2020 design)
ITER-like variants for TF, CS, and PF coils (subcooled version wrt 2020 design)
Mechanical structures + auxiliary systems
For DEMO-LAR baseline
Innovative variants for TF, CS and PF coils
ITER-like variants for TF and CS coils
Mechanical structures + auxiliary systems

## Slide 7
PF conductors: test of a PF Nb3Sn conductor
OK
OK
TF conductors: manufacture and test of RW5 conductor (Nb3Sn, 100kA, WST strand)
CS conductors: test of
  SECAS conductor
  CORC-like conductor
  NTNT conductor
For EDIPO: manufacture of coil demonstrators
For Insulation: manufacture and test of HV cold feedthrough
Activities to be completed in 2026:

## Slide 8: Delivarables shifted to 2026
MAG-T.02.02-T009-D001 | Investigation of High Voltage Insulation Samples | Nadezda Bagrets | 31/12/2023
MAG-T.02.02-T003-D004 | Industrial contract on the manufacture and test of samples done with the selected insulation material tolerant to Nb3Sn heat-treatment | Chiarasole Fiamozzi Zignani | 31/12/2024
MAG-T.02.02-T008-D002 | Manufacture and preliminary tests of the High Voltage Insulation Feedthrough for DEMO magnets | Luigi Morici | 31/12/2024
MAG-T.01.03-T004-D002 | Bendings of various empty RW jackets | Kamil Sedlak | 31/12/2024
MAG-T.02.02-T014-D001 | Investigation of High Voltage Insulation Samples | Nadezda Bagrets | 31/12/2024
MAG-T.01.01-T039-D001 | Procurements for the experimental setup | Achille Angrisani Armenio | 31/12/2024
MAG-T.02.02-T013-D003 | Manufacture of the High Voltage Insulation Feedthrough for DEMO magnets- VTT procurement | Anssi Laukkanen | 31/12/2025
MAG-T.01.01-T041-D001 | Microstructural characterisation of unpatterned and commercial filamentized REBCO tapes | Arend Nijhuis | 31/12/2025
MAG-T.01.01-T041-D002 | AC losses and interfilament resistance measurements of unpatterned and commercial filamentized REBCO tapes | Arend Nijhuis | 31/12/2025
MAG-T.01.01-T041-D003 | Characterisation of transport properties of REBCO tapes at 77K and in the range 4.2-10K, subjected to uniaxial tensile loading at varying magnetic field | Arend Nijhuis | 31/12/2025
MAG-T.01.01-T043-D001 | Purchase of a FIB-SEM equipped with EDS, EBSD and laser ablation chamber. | Angelo Vannozzi | 31/12/2025
MAG-S.01.03-T021-D002 | Setting-up a cryogenic apparatus for electromagnetic characterization of superconductors during neutron irradiation | Francesco Laviano | 31/12/2025
MAG-T.01.01-T045-D001 | EU-CN:Materials procurement for HTS conductors manufacturing_2025 | Achille Angrisani Armenio | 31/12/2025
MAG-T.01.01-T045-D003 | EU-CN: Manufacturing of HTS samples_2025 | Giuseppe Celentano | 31/12/2025
MAG-S.01.02-T007-D001 | R&D on double Jacket assembly for CS conductor | Xabier Sarasola | 31/12/2025
MAG-T.01.01-T048-D001 | RW5 sample assembly | Kamil Sedlak | 31/12/2025
MAG-T.01.01-T048-D002 | RW5 sample test in SULTAN | Jack Greenwood | 31/12/2025
MAG-T.01.01-T048-D003 | NTNT sample with improved soldering | Davide Uglietti | 31/12/2025
MAG-T.01.01-T048-D005 | Test of ENEA field-coupling setup | Nikolay Bykovskiy | 31/12/2025
MAG-T.01.01-T048-D007 | EU-CN: SULTAN test of ENEA HTS sample SECAS 2 | Mattia Ortino | 31/12/2025
MAG-T.01.01-T048-D008 | SULTAN test of CEA sample | Jack Greenwood | 31/12/2025
MAG-T.01.01-T048-D010 | Assembly and test of Lasso 3 coil | Nikolay Bykovskiy | 31/12/2025
MAG-T.01.01-T050-D001 | Mechanical and electro-mechanical tests | Nadezda Bagrets | 31/12/2025
MAG-T.01.01-T050-D003 | EU-CN: Survey and tests on stainless steel | Klaus Weiss | 31/12/2025
MAG-S.01.04-T023-D002 | Mechanical fatigue tests on a steel jacket ring | Francesco Giorgetti | 31/12/2025

## Slide 9: Project Deliverables not achieved
Deliverables 2024
InfoLink | Title | Deliverable owner
2S8Y3F | MAG-S.01.05-T002-D004-Population of the ENEA fusion component failure rate database. | Dongiovanni D. N.
2S8Q6X | MAG-S.02.02-T006-D001-Further development on quench detection with optical fibers | Greenwood J.
2S8ZPD | MAG-T.01.01-T018-D008-EU-CN:NTNT sample with improved soldering | Uglietti D.
2S8TNE | MAG-T.01.01-T018-D009-Purchase of the material for the PF conductor prototype (RW7) | Sedlak K.
2S8ZB3 | MAG-T.01.01-T018-D011-Cabling of various RW cable prototypes | Sedlak K.
2S8QFB | MAG-T.01.01-T018-D012-Small superconducting switch made of MgB2 | Bykovskiy N.
2S8V57 | MAG-T.01.01-T018-D013-RW5 sample assembly and test | Greenwood J.
2S8NN7 | MAG-T.01.01-T018-D016-SULTAN test of ENEA field-coupling setup | Bykovskiy N.
2S9PSD | MAG-T.01.01-T039-D001 - Materials procurement for the experimental setup | Angrisani Armenio A.
2S8X86 | MAG-T.01.01-T040-D003-EU-CN: Manufacturing of HTS samples_2024 | Celentano G.
2S8ZCL | MAG-T.04.01-T002-D001-Manufacture of the EDIPO II subscale coil | Greenwood J.
2S9368 | MAG-T.04.01-T002-D002-Assembly and SULTAN test of the EDIPO II subscale coil | Greenwood J.
2S94NQ | MAG-T.04.03-T001-D002-Procurement of Nb3Sn strand for the insert coil in CSMC | Sarasola X.
2S8YSK | MAG-T.04.01-T002-D003-Testing in SULTAN of the properties of EDIPO II R&W cable | Greenwood J.
2S8MGK | MAG-T.04.01-T002-D004-AC loss measurement of EDIPO II cable stack | Greenwood J.

## Slide 10: Project Deliverables deadlines
For Deliverables 2024 please upload the reports as soon as possible.
The placeholders for Deliverables 2025 are in IMS, in the folder «Deliverables 2025»:
https://idm.euro-fusion.org/default.aspx?uid=2SL8XM
Please upload the reports by February 2026

## Slide 11: Work Plan for 2026-27
2026-27 Activities
Manufacture and test of R&W Nb3Sn conductors (PF and CS SULTAN samples, and 100 m long conductor for the Central Solenoid).
Test of High Voltage cold feedthrough prototypes.
Manufacture of HTS conductors (SULTAN samples and 50 m long HTS conductor).
SULTAN tests of manufactured conductors.
Analysis of Experimental results.
X-ray tomography of Superconducting samples to check manufacturing defects.
Assessment of REBCO striated tapes, through microstructural characterisation, AC losses measurements and characterisation of transport properties of REBCO samples subjected to uniaxial tensile loading.
Study of the dynamic suppression of the superconducting state due to nuclear load by cryogenic in-situ measurements in a fusion reactor emulated environment.
Study of the effect of neutron and gamma irradiation on HTS tapes in conditions relevant for a fusion environment, to assess the conductor performance degradation.

## Slide 12: Grant deliverables
ID | Deliverables Table | Date | Comments
MAG.D.04 | Report on Magnet system design and analysis | 31.12.25 | In preparation
MAG.D.08 | Performance evaluation report on the CS conductor concept | 31.12.25 | In preparation
MAG.D.09 | Performance evaluation report on the PF conductor concept | 31.12.26 | 
MAG.D.11 | Performance evaluation report on the insulation systems | 31.12.26 | 
MAG.D.06 | Report on the manufacturing of the 100m long R&W conductor sample | 31.12.27 | 
MAG.D.07 | Report on the manufacturing of the 50m long HTS conductor sample | 31.12.27 | 
 | Report on the assessment of microstructural and transport characteristics of striated REBCO tapes | 31.12.27 | 
 | Report on the effect of irradiation on HTS superconducting tapes | 31.12.27 | 
The template for grant Deliverables is available at https://idm.euro-fusion.org/?uid=2N3G6V

## Slide 13: Grant milestones
ID | Milestones Table | Date | Comments
MAG.M.02 | Prototype cable and coil demonstrators for the EDIPO rebuilt magnet | 31.12.25 | In progress
MAG.M.09 | CS conductor concept completed | 31.12.25 | In progress
MAG.M.10 | PF conductor concept completed | 31.12.26 | 
MAG.M.12 | Insulation system concept completed | 31.12.26 | 
MAG.M.07 | 100m of R&W Nb3Sn conductor manufactured | 31.12.27 | 
MAG.M.08 | 50m of HTS conductor manufactured | 31.12.27 | 
 | Assessment of microstructural and transport characteristics of striated REBCO tapes | 31.12.27 | 
 | Assessment of irradiation effects on HTS superconducting tapes | 31.12.27 | 
Grant Milestones don’t require a report.

## Slide 14: Resources for 2026 (still under approval of GA)
Beneficiary | Year | PM @ 0% | PM @50% | PM @ 70% | Eq./OGS @ 0% [k€] | Eq./OGS @ 40% [k€] | Eq./OGS @ 70% [k€]
CEA | 2026 |  | 13 |  |  | 85 | 
CIEMAT | 2026 |  | 3 |  |  | 6 | 
CU | 2026 |  | 5 |  |  |  | 
DIFFER | 2026 |  | 14 |  |  | 35 | 
ENEA | 2026 |  | 28 | 10.8 |  | 658 | 
EPFL | 2026 |  | 12 | 5 |  | 740 | 240
IAP | 2026 |  | 3 |  |  | 10 | 
IPP.CR | 2026 |  | 4 |  |  |  | 
IPPLM | 2026 | 1.2 | 4 |  | 3.1 |  | 
OEAW | 2026 |  | 5 |  |  |  | 
UKAEA | 2026 |  | 22* |  |  |  | 
Additional resources 2026 for the EU-CN collaboration:
Missions for Best Preparation: 9k€
Missions for Attending the CS coil test campaign: 25k€
48 PM for Technological activities agreed with ASIPP + BEST Integrated Commissioning Plan Development
270 k€ EQ/OGS for Technological activities agreed with ASIPP
*UKAEA budget is self-funded

## Slide 15: Perspectives for 2026-27 EU-CN collaboration extension
Alternative methods for quench detection in HTS magnets
Continuation of mechanical tests and modelling of HTS superconducting conductors （REBCO +BISSCO)
Modelling of AC losses and transport properties of full-scale HTS conductors
X-ray tomography of HTS Superconducting samples (1 CORC subcable virgin or after load, joints of ENEA sample)
Study high strength stainless steel properties (Incoloy)
Attending CS coil testing in 2026
AC losses reduction (possible tests in CSMC of HTS conductors)
Quench test of CORC in SULTAN
Superconducting switch for quench protection

## Slide 16: Task Specifications 2026
Please send me Task specifications proposals by 13th February 2026.
We need time to agree on the content/budget and then all TS will be uploaded on IMS by Federico Quagliata Tamisari and myself by end of February.
Remember: to avoid cost rejection from the Commission, the description of each task/deliverable should include all required details. In particular:
name and schedule of the Facility (include Marina Ricci as a Reviewer)
For OGS, include what you need to buy. Specify equipment and consumables
Task specifications Template for TS 2026

## Slide 17: WPMAG Meetings
For the WPMAG Final Meeting 2025 please upload your presentation on the INDICO website:
https://indico.psi.ch/event/18303/timetable/#20260114
Loging with your indico account
In correspondence of your presentation you have a pen and a drop-down menu. Go under «Material Editor» and upload your file.
Next WPMAG Progress Meeting 2026 (on-line): October 2026
I will send a doodle to fix the dates.

## Slide 18
Thanks for your attention