## Slide 1: IMPACT
Overview IMPACT and Time schedule
Daniela Kiselev
IMPACT Informationsveranstaltung, PSI, 17.12.2025

## Slide 2: IMPACT: 18.12.24: Financing of IMPACT ensured!
Priority 1 also for SLS to reach the milestone user operation (~ mid25).
potential conflict of resources for SLS/IMPACT,
especially in shutdowns
Working group under the lead of the project office (M. Lüthy):
Goal: find solutions before the problem occur
  Evaluates available & needed resources
  Reports on resource bottlenecks
helpful in Q1/2025 SD of SLS & HIPA (+ IMPACT prep.)
General-Anzeiger 01/2025
Next:
SLS SD Q1-Q2/2026
In parallel to HIPA SD + IMPACT prep. work
By the Swiss Roadmap for Research Infrastructures 2025 – 2028
IMPACT is the large-scale project!
Project with highest strategic relevance for the period 2025–2028
(PSI Development plan 2025-2028, p. 23)
Notes: SLS SD 21.12.2025 – 4.5.2026
Upcoming events:
19.3.25 13:00 for project members:
Coffee, speech of director, Info talks, apero
Sept: 25: Info for all interested employees at PSI

## Slide 3: Project IMPACT = HIMB + TATTOOS
590-MeV- Ring
cyclotron
Particle physics
Material science
SINQ
TATTOOS
TgMHIMB
TgE
Life science
UCN
100 µA
> 2.2 mA protons
New building
HIMB: Muon flux * 100
1010 surface muons/s
Confirmed in realistic simulations!
TATTOOS: Radionuclides for cancer therapy and diagnostics (clinical studies)
Experimental hall
WEHA
= “Thera(g)nostics”
Courtesy of Mahir Dzambegovic
only for research application
(non-commercial)
New location
For He liquifier
New location for
tertiary water cycle 4 & 7
New beamlines MuH2&3
require extensive renovations
at WEHA with major changes
to the infrastructure
PiM1 MuH2
PiM3 MuH3

## Slide 4: Remodelling WEHA 2026
New exit
 Shorter emergency route
Now
End of 2026

## Slide 5: HIMB Layout (TDR): What is needed to operate HIMB & existing user facilities (”HIPA”)
590 MeV
protons
m+/-, p
28-80MeV/c
m+/-, p
28-60MeV/c
2 chicane
magnets
Exchange
flask H
19.5 m
11.5 m
Within shielding:
needs to be complete for HIPA operation
in addition:
re-assembly of PK1,
MuE4 and PiE1
PK1

## Slide 6: Timeline for final Decision Long Shutdown:
2025 |  |  |  | 2026 |  |  | 
Sept | Okt. | Nov. | Dez. | Jan. | Feb. | März | April
MuSR User Info
Retreat
Constraints:
Procurement
of energy for 2027
SINQ User Info
CHRISP User Info
8. SteCo
Pre-meeting
w. Director
27/28.
27.
10.
Info event (PSI)
17.
PM decision
Status talks
of work packages
20.

## Slide 7: (internal) Manufacturing
3 collimators
profile&position
monitor
movable slits
in dipoles
KHH0
KHH1
KHH2
MHP/S
10 t foot
50 t foot
6 types, 150 pieces
Signal rails
Collimator disks
Cooling plate

## Slide 8
2026
2033
HIMB
Milestones
Today
130 days
Jul 2 - Dec 31
523 days
Jan 1 - Jan 1
128 days
Jan 2 - Jun 30
2026
2027
2028
2029
2030
2031
Beam Com
367 days
Nov 12 - Apr 7
185 days
Apr 9 - Dec 23
User Op. HIMB
May 21 '30
2032
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
518 days
Jan 4 - Dec 27
66 days
Sep 28 - Dec 28
Oct 2
TATTOOS Concept
Start Shutdown
Oct 2 '27
HIMB Beam
Nov 2 '29
User Op
Sep 3 '29
TATTOOS Beam
Oct 16
2033
Q3
Q4
Q1
First p-Beam on TgH
1.7.2029
Dec 1
194 days
Sep 2 - May 30
105 days
Jun 2 - Oct 29
19 days
Nov 3 - Nov 30
131 days
Jan 2 - Jul 4
Dec 16
PSI Decision Building
Dec 27
Building appl.
Jan 1
Start Construction
20 days
Dec 3 - Dec 31
390 days
Jan 2 - Jun 30
Long Shutdown
178.5 days
Jan 2 - Sep 7
Dismounting
203.5 days
Sep 17 - Jun 28
Installation
219.5 days
Mar 31 - Feb 1
Pre-Assembly
137 days
Feb 18 - Aug 28
Exchange Flask Tests
Sep 30
May 31
Jan 5
Mar 31
Nov 25
Dec 2
Feb 16
Feb 1
Jun 11
Jul 9
Nov 9
Start User Op.)
Sep 3
Start HW Comm.
Mar 16
Start Installation
Oct 15
Tg M Dismantled
Jun 13
Start Tg M Dism.
Feb 11
248.5 days
Jan 1 - Dec 15
ATEC Tests
49.5 days
Oct 18 - Dec 24
Bl. Dism.
95.5 days
Jan 1 - May 14
SD '27
103.5 days
Jan 1 - May 26
SD '26
99.5 days
Jan 1 - May 20
SD '30
129.5 days
Jan 1 - Jul 1
SD '31
97.5 days
Jan 1 - May 17
SD '32
44.5 days
Jul 2 - Aug 31
.
86 days
Jan 4 - May 3
25 days
May 28 - Jun 30
.
Mar 31
149.5 days
Jan 7 - Aug 4
262.5 days
Aug 11 - Aug 11
18 Monate
Time schedule IMPACT & Milestones
TATTOOS
Building
Building Construction
Connection HIPA - TATTOOS
TATTOOS Installation
TATTOOS Comm.
Building Planning & Tendering
Building Pre-Project
.
Removal WMFA
Closing UCN Wall
Excavation pit incl. pillars
Shielding P-channel
UCN & Site preparation
.
.
interior finishing
LSD: shift by 1 y due to late delivery of essential components
+ 1y
Pre-SD for UCN, PiM1, PiM3, MuE4

## Slide 9: Pre-assembly before final installation
Consisting of : 5 vacuum chambers (BIG5) + inserts
+ 2 dipoles (ASP, ) incl. chamber
+ pillow seals
Additional time will be used for intensive tests
(vacuum, functioning) and pre-alignment
Advantages:
Pre-alignment of inserts in vacuum chamber
 saves time later
Faster installation on p-channel
 reduces personal dose
Early detection of failures (fitting, functioning)
 avoiding delays during installation
Remark: No test of exchange flask possible
due to floor load
Important;
Adjustments or mechanical refinishing are not possible
after irradiation due to high dose
Notes: not tested: Heating of the coil in vacuum chamber and possible influence on alignment
not clear;

## Slide 10: Site preparation: Making space for TATTOOS WMFA  TATTOOS building
Moving Proscan
ventilation
Relocation of
transformers
Shielding blocks & He compressors dismantled 2024
In addition:
Moving control room UCN to WNAB
Office, Labs WMFA  WLGA
Many electr. & cooling
infrastructure to be moved
Media tunnel
Moving D2-platform (50.5 t, red. 46.2 t) on UCN hall roof (WNAB) –> requires reinforcement & large crane (due to distance)
WMFA
WNAB
Dismantling Media channel
PSI Center for Accelerator Science and Engineering
Notes: Trafos: neue Plattform zwischen Speisgebäude und WEHA
Schwerster Kran Schweiz: 110 t Last, 52 m Ausleger

## Slide 11: Summary
Introduction to the PSI High Intensity Proton Accelerator (HIPA)
Extraction from the Ring Cyclotron
Beam transfer to the meson production targets M/E and SINQ spallation source
Beam diagnostics for setup & optimization
Feasibility study of beam rotation for SINQ
Beam switchover to the UCN source
Conclusion
Decision for shifting the long shutdown by 1 year. Beam on TgH: 1.7.2029
Time will be used for intensive tests of equipment.
Many infrastructure work to make space for HIMB and TATTOOS.
All goals like muon flux 1010/m/s confirmed by realistic simulations.
Great progress on the HIMB design moving from CDR to TDR
(Link coming soon).
Thanks to all contributing to IMPACT
CDR
TDR
https://www.psi.ch/de/impact

## Slide 12: IMPACT Collaboration event (19.3.2025)

## Slide 13: Organisation/Project structure IMPACT
5 centers involved!
CAS
CCS
CLS
CNM
NES
+ UZH & USZ:
no extra financial support
for IMPACT
Contribution UZH, USZ: Detector lab Demeter + Infrastructure for preparation of medical radionuclides
External Advisory Committees (EABs) for HIMB and TATTOOS: twice/year (each)

## Slide 14: Steps on the way to approval and financing
Seite 14
Swiss Roadmap .....
April 2021 2-page proposal: «Motivation & Intention», 1. cost estimate
Dez. 2021 SNF-Proposal: scientific motivation
Klaus Kirch, Roger Schibli, Ben Kilminster (UZH), Philipp Kaufmann (USZ)
Jan. 2022: Conceptional Design Report https://www.dora.lib4ri.ch/psi/islandora/object/psi%3A41209
July 2022: Scientific evaluation best marks!
Dec. 2022: Evaluation of techn. feasibility + finances
 ETH Board recommends IMPACT for Swiss Roadmap
June 2023: Publication of Swiss Roadmap
Jan. 2024: Implementation plan
Timeline, planning, spending profile, organization
March 2024: ETH Board supports financing of IMPACT
Final step:
Dec. 24: Decision of Swiss parliament about funding in 2025-2028
Swiss Roadmap for
Research Infrastructures
2025-2028 ERI Dispatch