## Slide 1: Status TATTOOS and preparatory work
Status 12/25
Robert Eichler :: On behalf of the team
Villigen PSI, IMPACT INFO Event, 17. December 2025

## Slide 2
2026
2033
TATTOOS
Building
Milestones
Today
130 days
Jul 2 - Dec 31
523 days
Jan 1 - Jan 1
128 days
Jan 2 - Jun 30
2026
2027
2028
2029
2030
2031
Building Construction
Connection HIPA - TATTOOS
367 days
Nov 12 - Apr 7
TATTOOS Installation
185 days
Apr 9 - Dec 23
TATTOOS Comm.
User Op. HIMB
May 21 '30
2032
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
518 days
Jan 4 - Dec 27
Building Planning & Tendering
66 days
Sep 28 - Dec 28
Building Pre-Project
Oct 2
TATTOOS Concept
Start Shutdown
Oct 2 '27
HIMB Beam
Nov 2 '29
User Op. (w/o MuH2, MuH3)
Sep 3 '29
TATTOOS Beam
Oct 16
2033
Q3
Q4
Q1
Dec 1
194 days
Sep 2 - May 30
.
105 days
Jun 2 - Oct 29
Removal WMFA
19 days
Nov 3 - Nov 30
Closing UCN Wall
131 days
Jan 2 - Jul 4
Excavation pit incl. pillars
Dec 16
PSI Decision Building
Dec 27
Building appl.
Jan 1
Start Construction
20 days
Dec 3 - Dec 31
Shielding P-channel
390 days
Jan 2 - Jun 30
178.5 days
Jan 2 - Sep 7
203.5 days
Sep 17 - Jun 28
219.5 days
Mar 31 - Feb 1
137 days
Feb 18 - Aug 28
Sep 30
May 31
Jan 5
Mar 31
Nov 25
Dec 2
Feb 16
Feb 1
Jun 11
Jul 9
Nov 9
Mar 16
Oct 15
Jun 13
Feb 11
248.5 days
Jan 1 - Dec 15
49.5 days
Oct 18 - Dec 24
95.5 days
Jan 1 - May 14
103.5 days
Jan 1 - May 26
99.5 days
Jan 1 - May 20
129.5 days
Jan 1 - Jul 1
97.5 days
Jan 1 - May 17
44.5 days
Jul 2 - Aug 31
86 days
Jan 4 - May 3
UCN & Site preparation
25 days
May 28 - Jun 30
Mar 31
149.5 days
Jan 7 - Aug 4
.
262.5 days
Aug 11 - Aug 11
.
Planung TATTOOS
TATTOOS
ONLINE
Purchase Manufacture
Technical design
Concept / Feasibility
.
WTOs
Infrastructure
3 Phases
Target/FE; Extraction/Ionization; Mass separation
TATTOOS
OFFLINE
Design validation, development
interior finishing

## Slide 3: TATTOOS Ambitions
produce upto 50 times more rare radionuclides compared to other running ISOL installations
have a recoverable target setup/module (less waste & operation budget)
operate tantalum targets in monthly rhythm
24 h target exchange
element specific laser resonance ionization (less isobar contamination)
mass separation factor 1500-2000 at ion beam currents of ~10A
storage of used targets for 2-3 years on site before disposal
Maintenance of larger components ~1/year (max)
enable a later upgrade to ThCx targets without major infrastructure rebuilt or costs
Place everything into the WMFA site

## Slide 4: Tattoos

## Slide 5: In-situ Dose & Shielding Target
Sv
Gamma ODL
Neutron ODL

## Slide 6: Thermal Release: thermodynamic considerations for Ta
Dose relevant for maintenance and handling
300 mm lead or 1 m heavy concrete or 2 m normal concrete

## Slide 7
Frontend Size and Handling @ TATTOOS
~4.5 m
120 t
12/16/2025
7

## Slide 8: Target Service Cell “TSC” (based on PSI-ATEC)
on site

## Slide 9: Building Concept Development - History
+ 11`000m³ Gebäudevolumen - Verdoppelung

## Slide 10: TATOOS Placement & Development
Preproject
Project
CDR

## Slide 11: Plan as of now (20.11.2025)
View towards Speisegebäude
Access
Separator & active storage
A-lab
Laser & HV & control room
C-Lab
Target &
Beam line
protons
Service cell
Disposal

## Slide 12: Latest Ion beam line design
Proton beam

## Slide 13
E
EG from top
Material Lock with material lift
Target steel
protons
E1
Material Lock with material lift
M2
M1
0
M1
Ions
Active storage /
cooling area
vertical
Movable
shielding
Movable
shielding
Storage
Cell

## Slide 14
Material Lock with material lift
May be a access for material
during construction of the shielded cells
(to be closed later)
A-LAB
A-LAB access
OG1 from top
E2
E3
vertical
M1
Ions

## Slide 15
Material Lock with material lift
Control room
C-LAB
Laser Lab
HV Room
Laser
OG2 from top

## Slide 16: Recent Hirings
Project position started October 2025
Tenure track:
Starting January 2026
Radionuclide Development group
Project position started October 2025
Permanent:
Starting January 2026
Target group
Experience from
Building
ISOLDE’s Offline 2
Many years of laser operation
At Mainz, CERN-ISOLDE
Robert House
Construction engineer
Timothy (Tim) Giles
Physicist
Dr. Reinhard Heinke
>25 years experience at ISOLDE
James Cruikshank

## Slide 17
FRONTEND Concepts

## Slide 18: Discussed solutions

## Slide 19: Offline TATTOOS Target/Frontend/Ion source Test Facility (OLT)
Found space in OTLA UG!
Phase 1 Target tests
Phase 2 Frontend & HV Tests
Phase 3 Ion production/RILIS
T/FE

## Slide 20: TATTOOS End 2025 Take Home
© PSI
https://www.psi.ch/en/impact
Further extremely valuable help from all PSI working groups needed
Technical challenges ahead and a lot of learnings!
Patience & know-how built-up required – Real Concept is only about to appear!
Delays in R&D due to delay of the priority and personnel hiring & know-how acquisition
Exciting science in radiopharmacy, radiochemistry and nuclear physics ahead with TATTOOS
A rocket launch costed>300M$ in 1980-90
Today it costs15-50 M$. This is in a scale
reachable for Switzerland!
Let’s launch!
Th. Zurbuchen (former NASA CSO)
@ ETH Domain conference @ EPFL 9.12.25