Startup summary
- Startup: rough timeline, main issues
- Lessons learnt for future startups
- SwissFEL at 6 GeV
- Status new meeting series (STC, SPM, SPP)
Thomas Schietinger
(with input from N. Hiller)
  SPM, 25 Sep. 2018

---
Startup summary – rough timeline
 Thursday, 13 September
  14:30 tunnel closing
  17:00 first electrons in gun
  21:30 beam up to BC1
 Friday, 14 September
  16:00 transmission to ECOL
  17:00 transmission to Aramis beamdump
  (No setup shifts on the weekend)
 Monday, 17 September
  18:00 reach design energy of 5.8 GeV
  19:00 first lasing at 9 keV (~15 µJ, random-walk optimization to 30 µJ)

---
Startup summary: main issues
Organizational issues:
- Startup strategy was not clear / changed during startup. Essentially two possibilities for an efficient startup:
  - restore previous setting as much as possible (laser profile, RF voltages, etc.) then apply changes or
  - start with new settings, but then set up the machine systematically from scratch (which takes time).
        In our planning, we allocated time for a quick restore, but then decided to start with a different
        laser profile, different energy profile etc. – a recipe for disaster!
- Due to the lack of a clear and consistent startup strategy, the startup did not result in a reliable, stable FEL setup, but some intermediate, poorly understood state. It then takes additional time to arrive at a stable setup.
- Manpower and time allocation: an adequate number of people should be on shift during startup. Need to allocate people from operations and beam dynamics on fix startup shifts.
Technical issues:
- Lots of trouble with moving parts: many motors not homed (power cut between pre-beam setup/checks and actual startup...)
- Numerous recurring problems with RF stations:
  - Multipactoring in klystrons (unstable operating regions)
  - Fake oil-level alarms
  - Modulator communication problems
- No fast and easy way to calibrate RF stations.
- A lot of software was broken during the shutdown...
  - Old versions should remain readily accessible
  - New versions should only be released after thorough testing!

---
Lessons learnt for future startups (1)
- Allocate sufficient time and manpower for setup and characterization of the machine (see next slide).
- Agree on a startup strategy: restore previous setting, or set up with new settings from scratch? Allocate resources accordingly.
- Startup checklist by operations (N. Hiller)
  - applied for the first time now, looks very promising!
  - can be split in three for efficient parallel processing by operators (e.g. RF stations, diagnostics, magnets and moving parts)
  - should be started in the morning, when experts can be reached!
  - whoever finishes first gets rewarded by running the gun-laser setup routine!
- Software necessary for the startup/setup should be checked beforehand.
  - clear communication of changes during the shutdown
  - thorough testing before startup!
- RF problems / instabilities: extremely annoying during startup – simply wait a few hours / half a day until most stations are in stable running, before setting up beam?
- Script to run RF calibration on all stations...

---
Lessons learnt for future startups (2)
After every multi-week shutdown, the planning must foresee ~4 days of set up work during working days (to reach expert groups)!
⇒ 8 “blue shifts” in DUO / Google calendar:
- first 8 shifts by operations
  (system checks, transmission,
  RF calibration)
- second 8 shifts shared by
  operations and beam dynamics
  (optics, compression FEL setup)
- The goal of this startup period
  should be a reliable setup for
  lasing (basis for all following work)
- Important: no distractions for the
  people working on shifts!
~7:00
OP
OP
OP + BD
OP + BD
~14:00
OP
OP
OP + BD
OP + BD
~22:00
Tunnel closing

---
Almost 6 GeV!
- All RF stations on beam except S20CB04!
- Reach 5.98 GeV (energy collimator),
  with compression!
- Weak lasing at 0.1 nm (F. Löhl)
- (BAG limit is up to 7 GeV)

---
SwissFEL: new organization
        (for the time being...)
SwissFEL Strategy Board
(SSB)
meets every three months
SwissFEL Exchange Meeting
(SEM)
SwissFEL Progress Meeting
(SPM)
SwissFEL Prioritization Panel
(SPP)
Mon 13:00 (OKAA/1)
Tue 10:30 (WBGB/021)
Tue 10:30 (WBGB/021)
Consol. & devel. of SwissFEL (machine)
every two weeks, 60 min.
(alternating with SPP)
chair: F. Löhl, T. Schietinger,...?
participation: open meeting
agenda:
General machine info
Beam-time reports
Other reports (system status,
upgrade plans, new ideas etc.)
Schedule (info from operations,
brief discussion)
Experiment planning for SwissFEL
weekly, 30 min. (max.)
chair: alternating photonics-machine
participation: open meeting
agenda:
Photonics: review/preview of
experiments (criticism, requirements)
Machine status and outlook
Discussion (only brief exchange!)
Priorities for SwissFEL (machine)
every two weeks, 60 min.
(alternating with SPM)
chair: machine coordinator (F. Löhl)
participation: closed panel
agenda:
operations report (focus on priorities)
review and update of priority lists
(beam-time requests, soft- and
hardware requests)
SwissFEL Technical Coordination Meeting
(STC)
Mon 9:00 (WBGB/020)
weekly, 30 min.
chair: run coordinator of previous week
participants: expert groups, operation, run
coordinators
agenda: systems status (incidents, outages,
all system info relevant for operation)
incident table / agenda template for efficient handling
Scheduling
continual schedule updates by operation
weekly release of schedule (e-mail)?
no specific meeting (not very useful...)
brief report at progress meeting
“Daily business”
Mid-term strategy
Long-term
strategy

---
SwissFEL: new organization
        Status of meeting series
SwissFEL Strategy Board
(SSB)
meets every three months
SwissFEL Exchange Meeting
(SEM)
SwissFEL Progress Meeting
(SPM)
SwissFEL Prioritization Panel
(SPP)
Mon 13:00 (OKAA/1)
Tue 10:30 (WBGB/021)
Tue 10:30 (WBGB/021)
Kickoff postponed due to absences!
First meeting scheduled for
        8 October
from then on every week!
Meeting series started on
11 September
next meetings:
 9 October
23 October
 6 November
20 November
Meeting series started on
21 August
next meetings (closed panel):
16 October
30 October
13 November
27 November
(2 October cancelled due to absences)
OP
SwissFEL Technical Coordination Meeting
(STC)
Mon 9:00 (WBGB/020)
Meeting series started on
17 September
next meetings (weekly!):
 1 October
 8 October
15 October
Scheduling
continual schedule updates by operation
weekly release of schedule (e-mail)?
no specific meeting (not very useful...)
brief report at progress meeting
“Daily business”
Mid-term strategy
Long-term
strategy